## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-07-11
| End date | 2016-07-25
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
BUG: Problems with cursor when track is played | 3 | Find cause | Vanja Cvetković | 0 | Done | [14 empty] | 0
|  | Resolve problem | Vanja Cvetković | 1 | Done | [14 empty] | 0 | bar: Day 13
|  | Retesting | Đuro Nenadović | 1 | Done | [14 empty] | 0 | bar: Day 14
BUG: Clicking on a remove track does not stop playing file | 3 | Find cause | Đuro Nenadović | 1 | Done | [14 empty] | 0 | bar: Day 11
|  | Resolve problem | Đuro Nenadović | 1 | Done | [14 empty] | 0 | bar: Day 11
|  | Retesting | Vanja Cvetković | 1 | Done | [14 empty] | 0 | bar: Day 13
BUG: Problems with longer wav files | 5 | Find cause | Predrag Dimitrijević | 0 | Done | [14 empty] | 0
|  | Resolve problem | Predrag Dimitrijević | 2 | Done | Day 5: 2 | 0
|  | Retesting | Đuro Nenadović | 1 | Done | [14 empty] | 0 | bar: Day 7
Total effort | 11 |  |  | 8 |  | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 0
|  |  |  | Idealy left | 8 | 7.4286 | 6.8571 | 6.2857 | 5.7143 | 5.1429 | 4.5714 | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 2.6645e-15
|  |  |  | Actually left | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 0