## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-06-13
| End date | 2016-06-27
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Problems with longer wav files | 5 | Find cause | Predrag Dimitrijević | 0 | Done | [14 empty] | 0
|  | Resolve problem | Predrag Dimitrijević | 2 | In progress | [14 empty] | 2
|  | Retesting |  | 1 | To do | [14 empty] | 1
Sound replays when windows is out of desktop borders | 8 | Find cause |  | 5 | To do | [14 empty] | 5
|  | Resolve problem |  | 5 | To do | [14 empty] | 5
|  | Retesting |  | 1 | To do | [14 empty] | 1
Problems with cursor when track is played | 3 | Find cause | Vanja Cvetković | 0 | Done | [14 empty] | 0
|  | Resolve problem | Vanja Cvetković | 1 | In progress | [14 empty] | 1
|  | Retesting |  | 1 | To do | [14 empty] | 1
Too much clicking on track to add wav file cause System.ArgumentOutOfRangeException | 8 | Find cause | Đuro Nenadović | 5 | To do | [14 empty] | 5
|  | Resolve problem |  | 2 | To do | [14 empty] | 2
|  | Retesting |  | 1 | To do | [14 empty] | 1
Total effort | 24 |  |  | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  |  | Idealy left | 24 | 22.2857 | 20.5714 | 18.8571 | 17.1429 | 15.4286 | 13.7143 | 12 | 10.2857 | 8.5714 | 6.8571 | 5.1429 | 3.4286 | 1.7143 | 0
|  |  |  | Actually left | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24