## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Lead Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-04-08
| End date | 2016-04-22
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Implement tracks functionality | 8 | Expand timeline for tracks | Vanja Cvetković | 0 | Done | [14 empty] | 0
|  | Implement single track serial play | Predrag Dimitrijević | 2 | In progress | [14 empty] | 2
|  | Implement multiple track paralel play | Vanja Cvetković | 4 | In progress | [14 empty] | 4
|  | Implement file chooser per track | Vanja Cvetković | 0 | Done | [14 empty] | 0
|  | Review code | Đuro Nenadović | 1 | In progress | [14 empty] | 1
|  | Implement select button for track |  | 2 | To do | [14 empty] | 2
|  | Implement adding new track to timeline | Vanja Cvetković | 0 | Done | [14 empty] | 0
Design buttons faces for GUI | 5 | Design and implement buttons design |  | 5 | [15 empty] | 5
|  | Review design |  | 1 | [15 empty] | 1
Improve GUI design | 13 | Add volume control to side panel |  | 3 | [15 empty] | 3
|  | Improve menu to folow chosen design |  | 2 | [15 empty] | 2
|  | Implement cursor for seeking timeline |  | 8 | [15 empty] | 8
|  | Review designs |  | 1 | [15 empty] | 1
Total effort | 26 |  |  | 29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
|  |  |  | Idealy left | 29 | 26.9286 | 24.8571 | 22.7857 | 20.7143 | 18.6429 | 16.5714 | 14.5 | 12.4286 | 10.3571 | 8.2857 | 6.2143 | 4.1429 | 2.0714 | -7.9936e-15
|  |  |  | Actually left | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29