## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-06-27
| End date | 2016-07-11
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
BUG: Not changing color of component while changing theme | 5 | Find cause | Đuro Nenadović | 3 | Done | Day 5: 3 | 0
|  | Implement fix | Đuro Nenadović | 2 | Done | Day 5: 2 | 0
|  | Retest | Đuro Nenadović | 1 | Done | [14 empty] | 0 | bar: Day 6
Add support for other sound file formats | 8 | Find libraries and methods for implementation | Đuro Nenadović | 2 | Done | Day 12: 2 | 0
|  | Implement conversion | Đuro Nenadović | 5 | Done | Day 14: 5 | 0
|  | Retest and review | Đuro Nenadović | 2 | Done | Day 14: 2 | 0
Total effort | 13 |  |  | 15 |  | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 7 | 0
|  |  |  | Idealy left | 15 | 13.9286 | 12.8571 | 11.7857 | 10.7143 | 9.6429 | 8.5714 | 7.5 | 6.4286 | 5.3571 | 4.2857 | 3.2143 | 2.1429 | 1.0714 | 3.1086e-15
|  |  |  | Actually left | 15 | 15 | 15 | 15 | 15 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 0