## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Lead Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-05-30
| End date | 2016-06-13
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Problems with longer wav files | 5 | Find cause | Predrag Dimitrijević | 0 | Done | [14 empty] | 0
|  | Resolve problem | Predrag Dimitrijević | 2 | In progress | [14 empty] | 2
|  | Retesting |  | 1 | To do | [14 empty] | 1
Sound replays when windows is out of desktop borders | 8 | Find cause |  | 5 | To do | [14 empty] | 5
|  | Resolve problem |  | 5 | To do | [14 empty] | 5
|  | Retesting |  | 1 | To do | [14 empty] | 1
Problems with cursor when track is played | 3 | Find cause | Vanja Cvetković | 0 | Done | [14 empty] | 0
|  | Resolve problem | Vanja Cvetković | 1 | In progress | [14 empty] | 1
|  | Retesting |  | 1 | To do | [14 empty] | 1
Too much clicking on track to add wav file cause System.ArgumentOutOfRangeException | 8 | Find cause | Đuro Nenadović | 5 | To do | [14 empty] | 5
|  | Resolve problem |  | 2 | To do | [14 empty] | 2
|  | Retesting |  | 1 | To do | [14 empty] | 1
Replacing sound file doesn't change loaded sound inside track | 3 | Find cause | Vanja Cvetković | 0 | Done | [14 empty] | 0
|  | Resolve problem | Vanja Cvetković | 1 | To do | [14 empty] | 1
|  | Retesting |  | 1 | To do | [14 empty] | 1
Total effort | 27 |  |  | 26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
|  |  |  | Idealy left | 26 | 24.1429 | 22.2857 | 20.4286 | 18.5714 | 16.7143 | 14.8571 | 13 | 11.1429 | 9.2857 | 7.4286 | 5.5714 | 3.7143 | 1.8571 | -5.7732e-15
|  |  |  | Actually left | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26