## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-03-20
| End date | 2016-04-03
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Create app marketing design | 8 | Create app logo | Đuro Nenadović | 3 | In progress | [14 empty] | 2 | bar: Day 3
|  | Design app gui | Vanja Cvetković | 5 | Done | Day 3: 5 | 0
|  | Review designs |  | 1 | To do | [14 empty] | 1
Write documetation for proffesor | 8 | Description project documentation | Predrag Dimitrijević | 3 | To do | [14 empty] | 3
|  | Requirements documentation |  | 3 | To do | [14 empty] | 3
|  | Architecture documentation |  | 3 | To do | [14 empty] | 3
Implement tracks functionality | 20 | Expand timeline for tracks | Vanja Cvetković | 5 | In progress | [14 empty] | 5
|  | Implement single track serial play |  | 5 | To do | [14 empty] | 5
|  | Implement multiple track paralel play |  | 5 | To do | [14 empty] | 5
|  | Implement file chooser per track |  | 1 | To do | [14 empty] | 1
|  | Implement adding new track to timeline |  | 3 | To do | [14 empty] | 3
Total effort | 36 |  |  | 37 |  | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
|  |  |  | Idealy left | 37 | 34.3571 | 31.7143 | 29.0714 | 26.4286 | 23.7857 | 21.1429 | 18.5 | 15.8571 | 13.2143 | 10.5714 | 7.9286 | 5.2857 | 2.6429 | 0
|  |  |  | Actually left | 37 | 37 | 37 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31