## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Lead developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-03-05
| End date | 2016-03-19
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Playing music and flow control | 13 | Find library that implements play functionality | Đuro Nenadović | 2 | Done | Day 3: 2 | 0
|  | Implement play functionality | Predrag Dimitrijević | 8 | Done | Day 7: 4; Day 8: 4 | 0
|  | Review code | Vanja Cvetković | 2 | Done | [14 empty] | 0 | bar: Day 9; Day 12
|  | Document implementation | Predrag Dimitrijević | 3 | In progress | [14 empty] | 2 | bar: Day 12
Implement basic GUI | 8 | Create flow controls and buttons | Vanja Cvetković | 2 | Done | [14 empty] | 0 | bar: Day 1; Day 4
|  | Implement file chooser | Vanja Cvetković | 2 | Done | Day 4: 2 | 0
|  | Timeline | Vanja Cvetković | 5 | In progress | [14 empty] | 4 | bar: Day 12
|  | Review code | Đuro Nenadović | 2 | Done | [14 empty] | 0 | bar: Day 9 to Day 10
|  | Document implementation | Vanja Cvetković | 3 | In progress | [14 empty] | 2 | bar: Day 12
Total effort | 21 |  |  | 29 |  | 1 | 0 | 2 | 3 | 0 | 0 | 4 | 4 | 2 | 1 | 0 | 4 | 0 | 0 | 8
|  |  |  | Idealy left | 29 | 26.9286 | 24.8571 | 22.7857 | 20.7143 | 18.6429 | 16.5714 | 14.5 | 12.4286 | 10.3571 | 8.2857 | 6.2143 | 4.1429 | 2.0714 | -7.9936e-15
|  |  |  | Actually left | 29 | 28 | 28 | 26 | 23 | 23 | 23 | 19 | 15 | 13 | 12 | 12 | 8 | 8 | 8