## Backlog user stories
Id | User Story name | Priority | Status | Note | Effort
1 | Create app marketing design | Low | Completed | Logo and basic appereance | 8
2 | Write documetation for proffesor | Medium | Completed | Documentation template that professor requires | 8
3 | Playing music and flow control | High | Completed | Basic audio file playing | 13
4 | Implement basic GUI | High | Completed | Basic GUI required for further development | 8
5 | Implement tracks functionality | High | Completed | Implementing tracks for audio mixing (multiple audio playing) | 20
6 | Improve GUI design | Medium | Completed | Redesign buttons and GUI in general | 13
7 | Design buttons faces for GUI | Low | Completed | Redesign buttons in png format | 5
8 | Implement final GUI design | Medium | In progress | Custom, designed, implementation of GUI | 20
9 | Replacing sound file doesn't change loaded sound inside track | High | In progress | - | 3
10 | Too much clicking on track to add wav file cause System.ArgumentOutOfRangeException | Medium | In progress | Probably because dobule clicked on same position | 8
11 | Problems with longer wav files | High | In progress | Play stops after some time | 5
12 | Sound replays when windows is out of desktop borders | Low | In progress |  | 8
13 | Problems with cursor when track is played | High | In progress | Cursor is going fast and out of app window | 3
14 | Implement themes | Low | In progress | Visual color themes (minimum two) | 8
15 | Create virtual MIDI keyboard | Low | Not sprint ready | Create keyboard for playing custom melodies and implement them in track | 40
16 | Implement project file format | High | Not sprint ready | Save and open project file custom format (.matf) | 20
17 | Exporting project to popular audio formats | Medium | Not sprint ready | Exporting mixed audio file | 20
18 | Implement install shield wizard | Medium | Not sprint ready | Installing app | 13
19 | Write documetation for proffesor (detailed) | Medium | Sprint ready | Detailed documentation that professor requires | 8
20 | Add support for other sound file formats | Medium | Sprint ready | For mp3, ogg, ac3, aiff, wma etc | 8
21 | Add scrolling to track | Medium | Sprint ready | While changin windows size, track is deforming (no scrollability) | 13
22 | Implement speed slider | Low | Sprint ready | Implement slider to control bpm of the song | 13
23 | Problems with wav file format | Medium | Sprint ready | Should implement normalizer of wav files | 13
23 | Implement various sound effects | High | Sprint ready | Changing of frequency, etc... | 20