## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-03-20
| End date | 2016-04-03
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Create app marketing design | 8 | Create app logo | Đuro Nenadović | 3 | Done | Day 3: 1; Day 6: 2 | 0
|  | Design app gui | Vanja Cvetković | 5 | Done | Day 3: 5 | 0
|  | Review designs | Predrag Dimitrijević | 1 | Done | [14 empty] | 0 | bar: Day 9
Write documetation for proffesor | 8 | Project description documentation | Predrag Dimitrijević | 3 | Done | Day 9: 3 | 0
|  | Requirements documentation | Đuro Nenadović | 3 | Done | Day 8: 3 | 0
|  | Architecture documentation | Đuro Nenadović | 3 | Done | Day 8: 3 | 0
Implement tracks functionality | 20 | Expand timeline for tracks | Vanja Cvetković | 5 | Done | Day 6: 1; Day 7: 3; Day 8: 1 | 0
|  | Implement single track serial play | Predrag Dimitrijević | 5 | In progress | Day 9: 2 | 3
|  | Implement multiple track paralel play | Vanja Cvetković | 5 | In progress | [14 empty] | 4 | bar: Day 9
|  | Implement file chooser per track | Vanja Cvetković | 1 | Done | [14 empty] | 0 | bar: Day 8
|  | Review code | Đuro Nenadović | 1 | In progress | [14 empty] | 1
|  | Implement adding new track to timeline | Vanja Cvetković | 3 | Done | Day 8: 3 | 0
Total effort | 36 |  |  | 38 |  | 0 | 0 | 6 | 0 | 0 | 3 | 3 | 11 | 7 | 0 | 0 | 0 | 0 | 0 | 8
|  |  |  | Idealy left | 38 | 35.2857 | 32.5714 | 29.8571 | 27.1429 | 24.4286 | 21.7143 | 19 | 16.2857 | 13.5714 | 10.8571 | 8.1429 | 5.4286 | 2.7143 | -1.1546e-14
|  |  |  | Actually left | 38 | 38 | 38 | 32 | 32 | 32 | 29 | 26 | 15 | 8 | 8 | 8 | 8 | 8 | 8