## Backlog user stories
Id | User Story name | Priority | Status | Note | Effort
16 | Implement project file format | High | Not sprint ready | Save and open project file custom format (.matf) | 20
29 | Design buttons to follow new themes | High | Not sprint ready | Create two versions of vector images, one for each theme | 8
17 | Exporting project to popular audio formats | Medium | Not sprint ready | Exporting mixed audio file (what can be read should be exported) | 20
18 | Implement install shield wizard | Medium | Not sprint ready | Installing app | 13
28 | All warning messages needs to be handled | Medium | Not sprint ready | Warning messages in code refer to unstable state. They needs to be handled. | 5
31 | Implement timescale for timeline | Medium | Not sprint ready | Timescale should simplify editing timeline, and enable user to put wav file to specific place | 8
15 | Create virtual MIDI keyboard | Low | Not sprint ready | Create keyboard for playing custom melodies and implement them in track | 40
13 | BUG: Sound replays when windows is out of desktop borders | High | Sprint ready | Replaying sound on maximize, changing size of app window, moving app window | 8
27 | Implement frequention changing per track | High | Sprint ready | Changing tone of the track inside track controls - referencing 24 and 15 | 8
19 | Write documetation for proffesor (detailed) | Medium | Sprint ready | Detailed documentation that professor requires | 8
21 | Add scrolling to track | Medium | Sprint ready | While changin windows size, track is deforming (no scrollability) | 13
23 | Problems with wav file format | Medium | Sprint ready | Should implement normalizer of wav files | 13
24 | Implement various sound effects | Medium | Sprint ready | Changing of frequency, etc... | 20
32 | BUG: Time progress label is starting even if no tracks is loaded | Medium | Sprint ready | It starts on pressing button play | 1
22 | Implement speed slider | Low | Sprint ready | Implement slider to control bpm of the song | 13
30 | Add support for custom sound file formats | Low | Sprint ready | Implement support for other audio file formats (wma, ogg, aac) | 13
12 | BUG: Problems with longer wav files | High | In progress | Play stops after some time | 5
14 | BUG: Problems with cursor when track is played | High | In progress | Cursor is going fast and out of app window | 3
26 | BUG: Clicking on a remove track does not stop playing file | Medium | In progress | Removing track leaves loaded track playing, can not stop, and disable it (referencing ?) | 3
11 | BUG: Too much clicking on track to add wav file cause System.ArgumentOutOfRangeException | Medium | Outdated | Probably because dobule clicked on same position | 8
3 | Playing music and flow control | High | Completed | Basic audio file playing | 13
4 | Implement basic GUI | High | Completed | Basic GUI required for further development | 8
5 | Implement tracks functionality | High | Completed | Implementing tracks for audio mixing (multiple audio playing) | 20
10 | BUG: Replacing sound file doesn't change loaded sound inside track | High | Completed | - | 3
2 | Write documetation for proffesor | Medium | Completed | Documentation template that professor requires | 8
6 | Improve GUI design | Medium | Completed | Redesign buttons and GUI in general | 13
8 | Implement final GUI design | Medium | Completed | Custom, designed, implementation of GUI | 20
20 | Add support for other sound file formats | Medium | Completed | For mp3, ogg, ac3, aiff, wma etc (mimimum mp3) | 8
1 | Create app marketing design | Low | Completed | Logo and basic appereance | 8
7 | Design buttons faces for GUI | Low | Completed | Redesign buttons in png format | 5
9 | Implement themes | Low | Completed | Visual color themes (minimum two) | 8
25 | BUG: Not changing color of component while changing theme | Low | Completed | Children component does not folow parent theme settings, save settings in file | 5
33
34
35

## Progress chart
Complete effort | Done | To do
349 | 127 | 211