## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-06-27
| End date | 2016-07-11
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
BUG: Not changing color of component while changing theme | 5 | Find cause | Đuro Nenadović | 3 | Done | Day 5: 3 | 0
|  | Implement fix | Đuro Nenadović | 2 | In progress | [14 empty] | 1 | bar: Day 5
|  | Retest | Đuro Nenadović | 1 | To do | [14 empty] | 1
Total effort | 5 |  |  | 6 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | Idealy left | 6 | 5.5714 | 5.1429 | 4.7143 | 4.2857 | 3.8571 | 3.4286 | 3 | 2.5714 | 2.1429 | 1.7143 | 1.2857 | 0.85714 | 0.42857 | 0
|  |  |  | Actually left | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2