## Backlog user stories
Id | User Story name | Priority | Status | Note | Effort
19 | Write documetation for proffesor (detailed) | Medium | Sprint ready | Detailed documentation that professor requires | 8
20 | Add support for other sound file formats | Medium | Sprint ready | For mp3, ogg, ac3, aiff, wma etc | 8
21 | Add scrolling to track | Medium | Sprint ready | While changin windows size, track is deforming (no scrollability) | 13
22 | Implement speed slider | Low | Sprint ready | Implement slider to control bpm of the song | 13
23 | Problems with wav file format | Medium | Sprint ready | Should implement normalizer of wav files | 13
24 | Implement various sound effects | Medium | Sprint ready | Changing of frequency, etc... | 20
26 | BUG: Clicking on a remove track does not stop playing file | Medium | Sprint ready | Removing track leaves loaded track playing, can not stop, and disable it (referencing ?) | 3
27 | Implement frequention changing per track | High | Sprint ready | Changing tone of the track inside track controls - referencing 24 | 8
12 | BUG: Problems with longer wav files | High | Sprint ready | Play stops after some time | 5
13 | BUG: Sound replays when windows is out of desktop borders | Low | Sprint ready |  | 8
14 | BUG: Problems with cursor when track is played | High | Sprint ready | Cursor is going fast and out of app window | 3
15 | Create virtual MIDI keyboard | Low | Not sprint ready | Create keyboard for playing custom melodies and implement them in track | 40
16 | Implement project file format | High | Not sprint ready | Save and open project file custom format (.matf) | 20
17 | Exporting project to popular audio formats | Medium | Not sprint ready | Exporting mixed audio file | 20
18 | Implement install shield wizard | Medium | Not sprint ready | Installing app | 13
28 | All warning messages needs to be handled | Medium | Not sprint ready | - | 5
29 | Design buttons to follow new themes and styles | High | Not sprint ready | Create vector images all color combinations | 13
25 | BUG: Not changing color of component while changing theme | Low | In progress | Children component does not folow parent theme settings, save settings in file | 5
11 | BUG: Too much clicking on track to add wav file cause System.ArgumentOutOfRangeException | Medium | Completed | Probably because dobule clicked on same position | 8
10 | BUG: Replacing sound file doesn't change loaded sound inside track | High | Completed | - | 3
1 | Create app marketing design | Low | Completed | Logo and basic appereance | 8
2 | Write documetation for proffesor | Medium | Completed | Documentation template that professor requires | 8
3 | Playing music and flow control | High | Completed | Basic audio file playing | 13
4 | Implement basic GUI | High | Completed | Basic GUI required for further development | 8
5 | Implement tracks functionality | High | Completed | Implementing tracks for audio mixing (multiple audio playing) | 20
6 | Improve GUI design | Medium | Completed | Redesign buttons and GUI in general | 13
7 | Design buttons faces for GUI | Low | Completed | Redesign buttons in png format | 5
8 | Implement final GUI design | Medium | Completed | Custom, designed, implementation of GUI | 20
9 | Implement themes | Low | Completed | Visual color themes (minimum two) | 8
30
31
32