## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-07-25
| End date | 2016-08-08
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
BUG: Sound doesn't play when it's not visible inside window | 8 | Find cause | Vanja Cvetković | 2 | Done | Day 11: 2 | 0
|  | Implement changes | Vanja Cvetković | 5 | Done | Day 12: 5 | 0
|  | Retest | Đuro Nenadović | 1 | Done | [14 empty] | 0 | bar: Day 13
BUG: Sound replays when windows is out of desktop borders | 8 | Find cause | Đuro Nenadović | 2 | Done | Day 3: 2 | 0
|  | Implement changes | Đuro Nenadović | 5 | Done | Day 5: 5 | 0
|  | Retest | Đuro Nenadović | 1 | Done | [14 empty] | 0 | bar: Day 6
Move edit buttons from Track to Timeline | 2 | Move buttons to Timeline | Predrag Dimitrijević | 1 | Done | [14 empty] | 0 | bar: Day 3
|  | Remove Select and Select actions move to Edit button | Predrag Dimitrijević | 1 | Done | [14 empty] | 0 | bar: Day 3
|  | Implement behaviour | Predrag Dimitrijević | 1 | In progress | [14 empty] | 1
|  | Retest for bugs | Đuro Nenadović | 1 | To do | [14 empty] | 1
Implement frequention changing per track | 8 | Research for way to implement | Predrag Dimitrijević | 2 | Done | Day 10: 2 | 0
|  | Implement functionality | Predrag Dimitrijević | 5 | In progress | Day 12: 2 | 3
|  | Retest for bugs |  | 1 | To do | [14 empty] | 1
Total effort | 26 |  |  | 28 |  | 0 | 0 | 4 | 0 | 5 | 1 | 0 | 0 | 0 | 2 | 2 | 7 | 1 | 0 | 6
|  |  |  | Idealy left | 28 | 26 | 24 | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
|  |  |  | Actually left | 28 | 28 | 28 | 24 | 24 | 19 | 18 | 18 | 18 | 18 | 16 | 14 | 7 | 6 | 6