## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-05-16
| End date | 2016-05-30
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Implement final GUI design | 20 | Find appropriate library or template | Đuro Nenadović | 3 | Done | Day 2: 3 | 0
|  | Implement already designed GUI elements | Đuro Nenadović | 5 | Done | Day 7: 4; Day 8: 1 | 0
|  | Implement already implemented functionalities | Đuro Nenadović | 13 | Done | Day 7: 10; Day 8: 3 | 0
|  | Code review | Vanja Cvetković | 1 | [15 empty] | 1
|  | Test for eventual bugs | Đuro Nenadović | 2 | In progress | [14 empty] | 2
Problems with longer wav files | 5 | Find cause | Predrag Dimitrijević | 3 | Done | Day 6: 3 | 0
|  | Resolve problem | Predrag Dimitrijević | 2 | In progress | [14 empty] | 2
|  | Retesting |  | 1 | [15 empty] | 1
Sound replays when windows is out of desktop borders | 8 | Find cause |  | 5 | [15 empty] | 5
|  | Resolve problem |  | 5 | [15 empty] | 5
|  | Retesting |  | 1 | [15 empty] | 1
Problems with cursor when track is played | 3 | Find cause | Vanja Cvetković | 2 | Done | Day 7: 2 | 0
|  | Resolve problem | Vanja Cvetković | 1 | In progress | [14 empty] | 1
|  | Retesting |  | 1 | [15 empty] | 1
Too much clicking on track to add wav file cause System.ArgumentOutOfRangeException | 8 | Find cause |  | 5 | [15 empty] | 5
|  | Resolve problem |  | 2 | [15 empty] | 2
|  | Retesting |  | 1 | [15 empty] | 1
Replacing sound file doesn't change loaded sound inside track | 3 | Find cause | Vanja Cvetković | 1 | Done | [14 empty] | 0 | bar: Day 7
|  | Resolve problem | Vanja Cvetković | 1 | [15 empty] | 1
|  | Retesting |  | 1 | [15 empty] | 1
Total effort | 47 |  |  | 56 |  | 0 | 3 | 0 | 0 | 0 | 3 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 29
|  |  |  | Idealy left | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
|  |  |  | Actually left | 56 | 56 | 53 | 53 | 53 | 53 | 50 | 36 | 32 | 32 | 32 | 32 | 32 | 32 | 32