## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-08-08
| End date | 2016-08-22
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Implement speed slider | 13 | Research strategy for implementation |  | 3 | To do | [14 empty] | 3
|  | Implement solution |  | 8 | To do | [14 empty] | 8
|  | Retest for bugs | Đuro Nenadović | 2 | To do | [14 empty] | 2
Add scrolling to track | 13 | Research strategy for implementation |  | 3 | To do | [14 empty] | 3
|  | Implement solution |  | 8 | To do | [14 empty] | 8
|  | Retest for bugs | Đuro Nenadović | 2 | To do | [14 empty] | 2
Move edit buttons from Track to Timeline | 2 | Move buttons to Timeline | Predrag Dimitrijević | 1 | To do | [14 empty] | 1
|  | Remove Select and Select actions move to Edit button | Predrag Dimitrijević | 0 | Done | [14 empty] | 0
|  | Implement behaviour | Predrag Dimitrijević | 0 | Done | [14 empty] | 0
|  | Retest for bugs |  | 1 | To do | [14 empty] | 1
Implement frequention changing per track | 8 | Research for way to implement | Predrag Dimitrijević | 2 | Done | [14 empty] | 2
|  | Implement functionality | Predrag Dimitrijević | 5 | In progress | [14 empty] | 5
|  | Retest for bugs |  | 1 | To do | [14 empty] | 1
Total effort | 36 |  |  | 36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
|  |  |  | Idealy left | 36 | 33.4286 | 30.8571 | 28.2857 | 25.7143 | 23.1429 | 20.5714 | 18 | 15.4286 | 12.8571 | 10.2857 | 7.7143 | 5.1429 | 2.5714 | -6.2172e-15
|  |  |  | Actually left | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36