## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-05-02
| End date | 2016-05-16
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Implement tracks functionality | 8 | Expand timeline for tracks | Vanja Cvetković | 0 | Done | [14 empty] | 0
|  | Implement single track serial play | Predrag Dimitrijević | 2 | Done | Day 7: 2 | 0
|  | Implement multiple track paralel play | Vanja Cvetković | 3 | Done | Day 7: 1; Day 14: 2 | 0
|  | Implement file chooser per track | Vanja Cvetković | 0 | Done | [14 empty] | 0
|  | Review code | Đuro Nenadović | 1 | Done | [14 empty] | 0 | bar: Day 14
|  | Implement select button for track | Vanja Cvetković | 2 | Done | Day 14: 2 | 0
|  | Implement adding new track to timeline | Vanja Cvetković | 0 | Done | [14 empty] | 0
Improve GUI design | 13 | Add volume control to side panel | Đuro Nenadović | 3 | Done | Day 14: 3 | 0
|  | Improve menu to folow chosen design |  | 2 | To do | [14 empty] | 2
|  | Implement cursor for seeking timeline | Vanja Cvetković | 8 | Done | Day 14: 8 | 0
|  | Review designs | Đuro Nenadović | 1 | In progress | [14 empty] | 1
Total effort | 21 |  |  | 22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 3
|  |  |  | Idealy left | 22 | 20.4286 | 18.8571 | 17.2857 | 15.7143 | 14.1429 | 12.5714 | 11 | 9.4286 | 7.8571 | 6.2857 | 4.7143 | 3.1429 | 1.5714 | -2.2204e-15
|  |  |  | Actually left | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 3