## Roster
Team roster
Name | Role | Index
Predrag Dimitrijević | Product owner | 1126/2015
Vanja Cvetković | Developer | 1125/2015
Đuro Nenadović | Scrum master | 1127/2015

## Sprint
| Start date | 2016-08-22
| End date | 2016-09-05
User story | Effort | Task | Asigned | Effort/per task | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Remaining
Implement timescale for timeline | 8 | Research way to implement | Vanja Cvetković | 3 |  | Day 12: 3 | 0
|  | Implement solution | Vanja Cvetković | 5 |  | Day 12: 5 | 0
|  | Retest Solution | Vanja Cvetković | 1 | [15 empty] | 0 | bar: Day 12
Design buttons to follow new themes | 8 | Implement designs | Đuro Nenadović | 2 | Done | Day 3: 2 | 0
|  | Find a way to scale images and design it that way | Đuro Nenadović | 3 | Done | Day 5: 3 | 0
|  | Redesign old designs | Đuro Nenadović | 3 | Done | Day 5: 3 | 0
Implement project file format | 20 | Research way to implement | Predrag Dimitrijević | 5 | Done | Day 5: 5 | 0
|  | Implement solution | Predrag Dimitrijević | 13 | Done | Day 7: 13 | 0
|  | Retest Solution | Predrag Dimitrijević | 2 | Done | Day 8: 2 | 0
Total effort | 36 |  |  | 37 |  | 0 | 0 | 2 | 0 | 11 | 0 | 13 | 2 | 0 | 0 | 0 | 9 | 0 | 0 | 0
|  |  |  | Idealy left | 37 | 34.3571 | 31.7143 | 29.0714 | 26.4286 | 23.7857 | 21.1429 | 18.5 | 15.8571 | 13.2143 | 10.5714 | 7.9286 | 5.2857 | 2.6429 | 0
|  |  |  | Actually left | 37 | 37 | 37 | 35 | 35 | 24 | 24 | 11 | 9 | 9 | 9 | 9 | 0 | 0 | 0